## Project Tracking
PROJECT TRACKING- Digital Signature Platform
PROJECTS
| AT RISK | STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | % DONE | ESTIMATED HOURS | STATUS KEY | PRIORITY KEY
|  | Complete | High | 1 week | Initial Discussion | Gather project team and Discuss ideas and reporting guide | 100% | 6 | Not Started | High
|  | Complete | Medium | 1 week | Topic Finalization & Feasibility study | Finalize the topic and get it approved from guide | 100% | 3 | In Progress | Medium
|  | In Progress | High | 1 week | Project Synopsis and Approval | Creating a detailed synopsis to outline project objectives | 100% | 8 | Complete | Low
|  | In Progress | Medium | 2-3 weeks | Requirements Gathering and Documentation | Gather requirements and create comprehensive documentation | 100% | 10 | On Hold
|  | Not Started | High | 1 week | System Design and Architecture | Design the system architecture and Interface | 60% |  | Overdue
|  | Overdue | Medium | 3 weeks | Development | Actual development of the plan | 50%
|  | On Hold | Low | 1 week | Testing | Testing and checking requirement satisfaction | 30%
|  | On Hold | Low | 2 weeks | Deployment & Implementation | Deploy the Project | 10%
|  | On Hold | Low | 1 week | Report Writing and Final Documentation | Final Documentation for submission | 80%

## Blank sheet
PROJECT TRACKING TEMPLATE
|  |  |  | PROJECTS |  |  | DELIVERABLE(S) |  | COST / HOURS
AT RISK | STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | DELIVERABLE | % DONE | FIXED COST | ESTIMATED HOURS | ACTUAL HOURS | STATUS KEY | PRIORITY KEY
[12 empty] | Not Started | High
[12 empty] | In Progress | Medium
[12 empty] | Complete | Low
On Hold
Overdue